## Slide 1: DIBC Request for Project Proposal (RPP) RPP-CM-26-01 Company Name: Nth Cycle Inc CAGE: 7Y0F0 UEI: KDEPLJUB1549 Project Title: Project SHIELD Anticipated Security Level: Unclassified, however Controlled Technical Information and/or Controlled Unclassified Information may be required.

## Slide 2
Proposed Solution
Company Viability and Expertise
Schedule of Major Milestones
Proposed Project (AOI 2) . Nth Cycle’s U.S. anchor black mass refining facility will intake 12,000 tonnes per year (tpy) of Li-ion battery black mass and produce 2,000 tpy nickel contained high-purity metal hydroxide, 4,000 tpa graphite, and 1,500 tpy battery grade lithium carbonate.
Unique Solution. Nth Cycle's proprietary electroextraction technology replaces single-use chemical consumables with electricity and process salt water, which significantly reduces operating costs classically associated with chemical consumption, water consumption, and liquid/solid waste production.
  Key Innovations. Reduces capital intensity by 70% at 5-10x smaller scale, solving the major pain point of traditional metal refining technology being too massive and expensive to build in the West
  Readiness Level. Starting TRL of 7/MRL 8, finishing at TRL 8/MRL 9
Nickel is critical to DOW because it supports advanced batteries and high-performance alloys needed for force readiness, defense manufacturing, and resilient installation energy systems, while reducing dependence on vulnerable foreign supply chains.
Graphite is critical to DOW because it is a foundational battery material, and the Department has used Defense Production Act authorities to expand domestic graphite production and processing in order to improve long-term supply chain resilience.
Project Schedule:
  The period of performance will be 36 months (Q2 2026 – Q2 2029)
Project Timeline:
  Feasibility, FEL2, and site selection underway with Fluor;
  Phase 1. Engineering, Permitting, & Planning (Q3 2026-Q3 2027);
  Phase 2. Construction (Q3 2027-Q4 2028);
  Phase 3. Commissioning (Q1 2029-Q2 2029).
Key deliverables and milestones:
  Final Investment Decision (Q3 2027);
  Major permits secured, include environmental permits (Q3 2027)
  Commercial Operation Date (Q2 2029).
A Rough Order of Magnitude (ROM) cost estimate for the Proposed Project is $235,000,000
  CAPEX ($160M); Corp Spend/Development ($65M); Assembly Facility ($10M)
We hired a financial advisor and have commenced a deSPAC, which we expect to close by Nov 2026. Expected proceeds from transaction are >$200M, and through a combination of this corporate equity and debt we will cover our cost share
Proprietary
Critical Raw Material Supply Chain Relationships. Black mass feedstock term sheets with Trafigura (12,000 tpa), WMC (3,000 tpa), Norsk Hydro/Hydrovolt (3,000 tpa), and Revomet (3,000 tpa).
Downstream Customer Relationships. Nth Cycle has a binding 10-year offtake agreement with Trafigura for all metal products produced from this facility secured (projected value of $1.1B).
Infrastructure and Facilities. Nth Cycle's headquarters are in Burlington, MA. Black mass refining demonstration facility in Fairfield, OH. Electroextraction stack assembly facility in Portsmouth, NH. Site visits around Charleston, SC have been completed to identify brownfield site for proposed commercial facility.
Supply Chain Integration
Company Overview. Nth Cycle is a critical minerals midstream refining company building the technology and infrastructure needed for Western supply chains. The company addresses the market's structural bottleneck: feedstock volumes do not align with the scale and economics of large, traditional refineries. Nth Cycle solves this constraint with a modular system, dramatically lowering capital intensity, deployment time and emissions to convert industrial scrap, black mass and primary feeds into intermediate and refined products within the nickel, cobalt, copper and rare earth value chains. These advancements enable the domestic production and allied partnerships vital to industrial competitiveness, national security and supply chain resilience.
Experience and Expertise. Nth Cycle has been operating its first commercial black mass refining demonstration facility in Fairfield, Ohio since 2024. Fundraising Summary. Raised >$80M to date. Commercialization Plan. We have a binding 10 year offtake agreement with Trafigura for products from this facility. Foreign Investment. Foreign investment is limited to a small number of investors who each own a low single digit % (max is 3.5% by a UK investor family office), a similar amount by Equinor, and lower amounts by other European and other investors. Total foreign ownership <15%.Non-compliance notices. None.